Office of the UN

Resident Coordinator Ethiopia

Implementation

of U.N. Assistance

to  the  War  Displaced

in Tigray and Afar Region

Update,   September 1998

DRAFT – 20/09/98

Contents

Implementation of Pledged Assistance

Food		Page  2

Health	Page  3

Water & Sanitation	Page  5

Shelter & Household	Page  6

Others	Page  7

(Note: all figures in US Dollars)

Implementation of pledged UN Assistance

In July, the UN Country Team in Ethiopia began implementing its assistance to people displaced by the Ethiopian-Eritrean conflict. An outline of the joint UN response was compiled in the document “War Displaced in Tigray and Afar Region, UN Response Summary”.

Agencies are presently engaged in emergency programmes for which funds were immediately available: a total of about $ 3 million.

The following pages give an update of the implementation of the emergency programme:

Food

WFP

a)	Assistance pledged

WFP has agreed to a reallocation  for Tigray region of  5,000 M/T of cereal under a previous emergency operation valued at $1.6 million.

b)	Implementation
DPPC has collected the total quantity except 223 M/T which remains in the EFSRA warehouse in Mekele. WFP will carry out a mission starting September 20th to the region to review the distribution plan for the grain.

In addition, WFP is arranging the shipment of 5 rubb-halls stores with a capacity of 500 – 800 M/T each as a contingency.

2.	Health

1) 	UNICEF

Assistance pledged

$190,000 ($171,000 for Tigray and $19,000 for Afar Region) out of the available $500,000 “Global Emergency Fund” have been allocated to an emergency health & nutrition intervention.  In addition, 50 Emergency Health Kits (38 for Tigray and 12 for Afar) have been reprogrammed in agreement with the government.

Plan of Activities and Implementation:

1.	Tigray:

During their field visit to Tigray in September, UNICEF has revised the initial emergency plan in the Health & Nutrition sector  according to the encountered needs . The new plan contains the following components:

Nutrition: 
Plan of Activities: Funds amounting to $57,500 have been allocated to set up a nutrition surveillance system by providing survey material (mainly weighing scales) and training.

Implementation: The weighing scales, which have been ordered from abroad, are expected for next week.

Extended programme for Immunization (EPI):

Plan of activities: The Regional Health Bureaux achieve a high immunization coverage among the regular and displaced population. There is no need to launch new vaccination campaigns. Instead, UNICEF plans to strengthen existing regional EPI services with additional cold chain equipment. Funds allocated: $52,600.

Implementation: The equipment has been ordered and is planned to arrive in the next three weeks.

Safe delivery:

Plan of activities: $69,000.- have been earmarked for the purchase of 200 Traditional Birth Attendant (TBA) Kits, for training of birth attendants and for follow up of the programme.

Implementation: The TBA kits have been ordered and will arrive within the next three weeks.

Malaria prevention and treatment:

The Regional Health Bureaux have requested assistance with medicine and malathion spray to tackle a serious malaria problem. UNICEF is seeking additional funds. For immediate action, limited funds have been advanced from General Resources (regular programmes).

Plan of activities: 400,000 tablets and 14,000 litres of malathion spray have been ordered, partly to replenish the existing stocks of the Regional Health Bureaux which were used for immediate action until the UNICEF material arrives.

Implementation: All material has been ordered. The tablets will arrive within the next three weeks by plane, the spray around November by ship.

Standard Health Kits

The Regional Health Bureaux have received the existing contribution of 38 kits destined to Tigray Region. UNICEF has requested information about further distribution of the kits.

Afar
Following a field mission mid-September to Afar Region, UNICEF is in the process of revising the plans of activity  prepared by the regional authorities .

2) 	WHO

Assistance pledged

WHO has delivered 10 Standard Emergency Kits to the Ministry of Health, donated by the Italian Government.

b)	Implementation:

Six kits have been transported to the Regional Health Bureaux in Tigray. The four kits destined to Afar region remain with the MoH in Addis Ababa and will be transported upon request of the Afar region. Afar is said to have sufficient stocks at present from other sources and they do not have enough storage facilities.

Water & Sanitation

UNICEF

Assistance pledged

$130,000 ($95,000 for Tigray and $35,000 for Afar Region) out of the $500,000 “Global Emergency Fund” have been earmarked for immediate action in the Water & Sanitation sector.

Plan of Activities and Implementation:

1.	Tigray:

UNICEF has set up the following activity plan in collaboration with the Regional Authorities:

Plan of Activities:

Water:
Plan of activities: Construction of 15 boreholes equipped with 15 hand-pumps to provide potable water to 7,500 displaced persons. The costs for the boreholes are covered with 60% ($65,490) by UNICEF and 40% by the regional government.  UNICEF will provide the hand-pumps from their local stock.

Implementation: The funds have been transferred to the Bureau of Water and Mines in Mekele.

Sanitation:
Plan of activities: Construction of 100 latrines as well as hygiene and education training for the total displaced population, including supply of laundry and soaps. Funds have been allocated in the amount of $28,064.

Implementation: The funds have been transferred to the Bureau of Health in Mekele.

Afar
The agency is in the process of revising the plans of activity for the Water & Sanitation sector prepared by the Regional Authorities.

Shelter and Household

1)	UNICEF

Assistance pledged

$40,000 ($26,800 for Tigray and $13,200 for Afar Region) out of the $500,000 “Global Emergency Fund” have been allocated to the Shelter and Household sector for the purchase of tarpaulin plastic sheets.

b)	Plan of Activities and Implementation:

Tigray and Afar region:

The 120 rolls of tarpaulin (80 for Tigray region and 40 for Afar region) have arrived in Addis Ababa airport. DPPC is in the process of clearing the material and will arrange transport it to the regions.

UNHCR

Assistance pledged

UNHCR has made available 3,000 kerosene stoves in the amount of $24,000.
In addition, UNHCR offers the following items out of its in-country stock:

1,680 kitchen sets for families

1,760 blankets

295 plastic sheets

1,660 buckets

480 knives

b)	Implementation:

DPPC’s distribution plan for the stoves and household equipment is currently under revision. After agreement, DPPC will collect the stoves and other supplies from the UNHCR stores.

OCHA

a)	Assistance pledged

On the recommendation of the UN Disaster Management Team in Ethiopia and in response to the official appeal from DPPC, a contribution of plastic sheeting and nylon rope was made by OCHA, financed with funds from the Italian government.

Implementation
The material has arrived at the Addis Ababa airport and has been cleared by DPPC.

Other Assistance

A.	Education

1)	UNICEF

a)	Assistance pledged

UNICEF has allocated $125,000 ($111,600 for Tigray and $13,400 for Afar Region) out of the $500,000 “Global Emergency Fund” to  emergency education.

Plan of Activities and Implementation

1.   Tigray

In collaboration with the Regional Education Bureau and the Zonal Education Departments UNICEF has set up the following activity plan:

Plan of Activities:

Orientation of 20 educational administrators/planners and 500 in-service teachers in 11 programmes with 500 participants and 40 resource persons.

Purchase of essential education material for 16,000  children.

Implementation: UNICEF has released the funds and the regional counterparts are preparing the organisation of activities. It is planned to start the workshops beginning of October.  UNICEF is processing the local purchase of the education material.

2.	Afar

Following a field mission mid-September to Afar Region, UNICEF is in the process of revising the plan of activities prepared by the Regional Authorities .

UNESCO

UNESCO has received approval to take $30,000 from its Programme for Emergency and Rehabilitation. Areas of assistance will be determined in collaboration with UNICEF and the local authorities.

Special Protection Needs

UNICEF

a)	Assistance pledged

UNICEF has earmarked $15,000 ($10,000 for Tigray and $5,000 for Afar Region) from the $500,000 “Global Emergency Fund” for an emergency programme in the sector of Special Protection Needs.

b)	Plan of Activities and Implementation

1.	Tigray

In collaboration with the Bureau of Labour and Social Affairs in Mekele, UNICEF has revised its initial plan of activities as follows:

Plan of Activities: To provide clothing (bed sheets, blankets etc.) and lodging to about 60 orphans; organise their transport from Adigrat to an orphan center in Mekele and ultimately organise a reunification with their family.
Implementation: the funds of $10,000 will be transferred to the Bureau of Labour and Social Affairs in Mekele within the next days.

2.	Afar

UNICEF will revise the plan of action proposed by the regional bureau and organise cash transfer.

Monitoring and Evaluation

UNICEF

With additional administrative funds UNICEF has set up an office in Mekele with a full time field officer and a secretary. A car and driver will be added to make the office fully operational. The office will serve as a field base for both, the emergency programme as well as the regular “Belgium Survival Fund” (BSF) programme .

# Footnotes

Copies of the report can be obtained at UNDP Emergencies Unit for Ethiopia, from UN Agencies or from OCHA in New York or Geneva.